## Sheet1
DATA 607 FINAL PROJECT TRACKER
Task ID | TaskName | Category | Date Added | Due Date | Owner | Owner2 | Status | Risk Level | Detail
1 | Submit Project Proposal | Writeup |  |  | Alex | Team | Completed | Green | Wrote and uploaded Proposal online.
2 | Discuss with Andy Caitlin | Presentation | 2019-05-03 |  | Team |  | Completed | Grey | Andy agreed project idea was promising. He suggested using human scoring to provide a benchmark to see if automated sentiment was effective in replicating human scores.
3 | Final Project Submission | Submission | 2019-05-03 | 2019-05-12 | Team |  | Not Started | Grey | Submit final project details
4 | Final Project Presentation | Presentation |  | 2019-05-15 | Team |  | Not Started | Grey | Discuss in class
5 | Collect Financial Time Series | Data Collection |  | 2019-05-07 | Arun |  | Completed | Green | [May 5]: AR agreed to email description of task update. Daily time series, specification of series names provided. Files to be uploaded to Github in DATA Folder in csv format. Provide email comment on structure of data file format. Dates in yyyymmdd format. Rates in percent format. Index levels in raw format. File names like FRED_<SeriesName>.csv
6 | FOMC Statement Collection | Data Collection | 2019-05-05 | 2019-05-07 | Jagdish |  | Active | Amber | [May 5]: JC scraped content in RMD posted to Github. FOMC contents to be available in RDATA object format so other team members can load into memory. Optional step: Each statement should be named as FOMC_<yyyymmdd>.txt. Exclude content like Open Market Implementation Notes. A Valid FOMC statement file should have roughly 5-6 paragraphs only. A sample FOMC_20190320.txt is provided for reference.
7 | Comment on RPUBS sample by Henry | Planning |  | 2019-05-05 | Alex |  | Completed | Green | Feedback provided. Files used were not FOMC statements.
8 | Outline Study Format | Planning | 2019-05-05 | 2019-05-06 | Alex | Jagdish | Active | Green | [May 5]: Agreed to limit initial scope to comparison of manually scored statement sentiment to automated sentiment. JG suggests completing phase 1 and doing write-up before progressing phase 2 as optional next step.
9 | Explain FOMC statements format/location | Data Collection |  | 2019-05-06 | Jagdish |  | Completed | Green | JC to talk HO through locations and samples of FOMC statements.
10 | Classify & Hand Label FOMC statements | Data Exploration |  | 2019-05-08 | Alex |  | Active | Amber | Identify statements manually by reading through them. Agree range of dates (2007-2019)
11 | Sentiment Analysis Module Review | Coding | 2019-05-05 | 2019-05-08 | Arun | Henry | Not Started | Grey | Identify if R sentiment analysis package is usable for Dictionary sentiment analysis to create a sentiment score. Read the vignette. https://cran.r-project.org/web/packages/SentimentAnalysis/vignettes/SentimentAnalysis.html
12 | Circulate Meeting Content | Data Collection | 2019-05-05 | 2019-05-05 | Alex |  | Active | Green | DateList in Excel and CSV format of FOMC dates between 2007-2019. Excel tracker

## Config
Category | Owner | Status | Risk Level
Coding | Alex | Active | Green
Data Collection | Arun | Pending | Amber
Data Exploration | Henry | Completed | Red
Data Wrangling | Jagdish | Cancelled | Grey
Modeling | Team | Not Started
Planning
Presentation
Research (Reading)
Submission
Writing